## POA&M Tracker
Finding ID | Control | Weakness | Risk Level | Recommended Remediation | Owner | Target Completion Date | Status | Validation Evidence
POAM-001 | SC-28 | BitLocker not enabled — system drives are unencrypted, leaving sensitive data at rest unprotected and accessible if the device is lost or physically accessed | CAT I | Enable BitLocker encryption on all Windows 11 system drives; configure BitLocker startup policy via Group Policy; verify encryption status using manage-bde or BitLocker Management console | System Administrator / IT Security Team | 30 Days | Open | BitLocker enabled confirmation via manage-bde -status output; Group Policy screenshot; SCC rescan showing SC-28 as pass
POAM-002 | IA-5 | Password length less than 14 characters — current password policy does not meet STIG minimum length requirement, increasing risk of credential compromise through brute force attacks | CAT II | Configure Group Policy to enforce minimum password length of 14 characters with complexity requirements enabled; verify policy application across all accounts | System Administrator | 30 Days | Open | Group Policy Management screenshot showing updated password policy; SCC rescan confirming IA-5 finding resolved; secpol.msc password policy configuration screenshot
POAM-003 | AC-7 | Account lockout duration below STIG requirement — current lockout duration is insufficient, allowing automated attacks to resume more quickly after triggering lockout | CAT II | Configure account lockout duration to 15 minutes or greater via Group Policy; verify lockout threshold and observation window settings also meet STIG requirements | System Administrator | 30 Days | Open | Group Policy Management screenshot showing updated lockout duration; secpol.msc account lockout policy screenshot; SCC rescan confirming AC-7 finding resolved
POAM-004 | AU-2 / AU-12 | Audit Account Logon failures not configured — logon failure events are not being captured, preventing detection of brute force attempts and unauthorized access activity | CAT II | Enable advanced audit policy settings via Group Policy to capture both success and failure events for Account Logon, Logon/Logoff, and Account Management categories | System Administrator | 15 Days | Open | Advanced audit policy screenshot via auditpol /get /category:*; Event Viewer confirming logon failure events (Event ID 4625) now generated; SCC rescan showing AU-2 and AU-12 resolved
POAM-005 | IA-2 | WinRM Basic Authentication enabled — allows credentials to be transmitted without encryption, exposing authentication credentials to interception on the network | CAT I | Disable Basic Authentication for WinRM service via Group Policy or registry settings; verify WinRM authentication configuration using winrm get winrm/config command after change | System Administrator / IT Security Team | 15 Days | Open | Registry or Group Policy screenshot confirming Basic Authentication disabled; winrm get winrm/config output showing AllowBasic = false; SCC rescan confirming IA-2 WinRM finding resolved
POAM-006 | CM-7 | Autorun enabled — allows removable media and external drives to execute automatically, creating significant risk of malware introduction through physical media attacks | CAT I | Disable Autorun and Autoplay for all drive types via Group Policy under Computer Configuration > Administrative Templates > Windows Components > AutoPlay Policies | System Administrator | 15 Days | Open | Group Policy Management screenshot showing Autorun disabled for all drives; registry confirmation of NoDriveTypeAutoRun setting; SCC rescan confirming CM-7 autorun finding resolved
POAM-007 | IA-5 | NTLM hardening not configured — system is not enforcing NTLMv2 authentication, leaving it vulnerable to pass-the-hash attacks and NTLM relay attacks on the network | CAT I | Configure LAN Manager Authentication Level via Group Policy to enforce NTLMv2 only and refuse LM and NTLM; set Network Security: LAN Manager Authentication Level to Send NTLMv2 response only | System Administrator / IT Security Team | TBD | Open | Group Policy or secpol.msc screenshot showing LAN Manager Authentication Level set to NTLMv2 only; SCC rescan confirming IA-5 NTLM finding resolved